## Slide 1
AUAR
Software Engineering Lead
Both features demo on 12 October.
At Risk: an unsupervised demo.
Delivery plan · two build slices · the reasoning behind both
You have read the repository. This session is for the calls that are contestable.
24
working days of pure sequence to an unsupervised demo
49%
over capacity as handed over, before anything goes wrong
1
question in week one decides the shape of the plan
Notes: "Both features will demo on 12 October. What's actually at risk is running it *unsupervised* — and that's decided by something neither feature touches. You've read the repo, so I'd rather spend this session on the calls that are contestable than walk you through the plan.” The three numbers are the whole story in miniature.

## Slide 2
A quick recap
A map of the argument, and where each part lives if you want to go back to it.
1
The critical path runs somewhere unexpected
Two chains converge on the cell re-test. Neither was traced end to end, and the longer one ends outside the company.
01-delivery-plan.md
2
One question in week one decides the plan's shape
Can firmware split so the stop path ships before the re-test and observability after? Plan A and Plan B branch from that answer.
03-demo-date-branch.md
3
The cuts are arithmetic, not preference
35.6 person-weeks of demand against 23.9. Every cut carries the number from the supplied data that justifies it.
01 · 05-estimation-calibration.md
4
Two things added, both from running the fixtures
Cost classification before approval, and the event schema contract that was missing. Neither was in the briefs.
stories.md · firmware-event-schema-v4.2.md
5
Drawing the schedule found what writing it missed
The resource pass turned up five things and reversed a recommendation. That reversal is in the repo, not tidied away.
06-b-pass-robotics.md
THE REPOSITORY
README.md
reading order
deliverables/
00 cto-response
the reply
01 delivery-plan
the plan
02 scope-decisions
12 calls
03 demo-date-branch
A / B
04 critical-path
diagram
05 estimation
multipliers
06 b-pass-robotics
the pass
stories.md
revised set
firmware-schema
the contract
code/
estop-audit
157 tests
panel-revision-impact
66 tests
Ten minutes: 00, then 04, then 03. That is the plan; everything else is the working.
Notes: Do not read this slide out. Give them fifteen seconds to re-orient, say the one line about the ten-minute path, and move on. Its real job is to be the slide you flip back to when someone asks where something lives.

## Slide 3
1
Two chains, one gate
Neither was traced end to end in the hand-over, and they converge on one event.
SOFTWARE CHAIN
a2 e-stop logging
a3 stop response
float — 9 days reserve
FIRMWARE CHAIN — binding
v4.2a stop path
bench
deploy
THE GATE
a5 cell re-test
a7 inspector — EXTERNAL, 10 working days
boards
arrive
THE WALL
Wed 23 Sep
DEMO
Mon 12 Oct
The inspection chain is easy to under-read
It looks like a list of small actions. End to end it is 24 working days of sequence, and the last 10 are an external lead time we do not control.
The firmware chain has two readings
The summary lands it at week 5; the detailed breakdown (2.5w + 1.0w + 0.5w from week 3) lands it at week 7. Worth reconciling early — this plan assumes the longer one.
Notes: The finding is not that either chain is long. It is that they aren’t traced end to end, and they meet at the cell re-test. Note the float on the software chain — that is why a2 is not, in the end, the binding constraint.
The software side finishes early and then waits; the firmware side is the one that actually binds. They meet at the cell re-test, and everything after that is a ten-working-day external lead time we don't control.
3bands, 1 timeline: the software chain across the top, the firmware chain in the middle, and the gate they both feed at the bottom. The grey block on the software row is nine working days of float — that's why a2 finishing early doesn't actually help, because the firmware chain is what binds. The red line is the wall: the last day we can submit to the inspector and still have a signed-off cell on 12 October." **If asked why the float is drawn at all:** it's the only reserve on that path, and showing it stops anyone filling it with work

## Slide 4
2
One question decides the shape
Asked in week one, before anyone has built anything. Not discovered in week six.
Q-A Can v4.2 split so the stop path ships first and observability ships after sign-off?
Q-B Can the run-event stream ride in the early half without extending its build?
Q-A asks whether the split is possible. Q-B asks whether it is worth having.
PLAN A — split works
Demo 12 Oct
Unsupervised
Certificate
Wed 7 Oct
Fleet Monitor real-cell integration
1 week
FM-4 buffer
Cut
Float on robotics chain
~1 day
PLAN B — split does not work
Demo 12 Oct
Supervised
Certificate
~Mon 2 Nov
Fleet Monitor real-cell integration
3+ weeks
FM-4 buffer
Ships
Float on robotics chain
~2 weeks
Recommendation: Plan B, unless both answers are yes. Plan A as originally scoped delivers an unsupervised demo of under-integrated software — and the under-integrated half is the feature the customer came for.
Notes: One question to Chris in week one decides which plan we're running. Q-A asks whether the firmware can split; Q-B asks whether that split is worth having. I'll be straight with you — my first answer here was Plan A, and drawing the resources changed it."

## Slide 5
3
What gives, and the number behind each
Demand as handed over: 35.6 person-weeks against 23.9 available. Roughly 49% over.
4.5
wks
Build model migration cutover
The week-3 target needs 4.5 calibrated weeks against 2.8 available before it, with weeks 4–5 out. Replaced by a read-only adapter; cutover moves to Q4.
2.3
wks
Indirect effects, as designed
Adjacency flags 13 of 20 panels on the real fixture, against a 12% waste baseline — it over-flags, which is the opposite of what the feature is for.
3.6
wks
Run-progress estimator
cycleSeconds does not reconcile with wall clock — 388s reported against 376s elapsed. Derive from panel counts instead.
0.7
wks
Operator sign-in (a4)
The only inspection action that does not block unsupervised running. run.started may already carry the data.
After cuts: ~21.4 against 23.9. About 10% slack, so the release valves are pre-agreed rather than found later.
Notes: Every cut has a number from the supplied data, not a judgement. The adjacency one is the sharpest: over-flagging is correct for a safety system and wrong for a cost-reduction tool, because over-flagging is the failure mode the feature was funded to prevent.

## Slide 6
4
What I added, and why it came from the data
Neither was in the hand-over. Both fall out of reading the fixtures.
PR-6 Impact and cost assessment
Seven of twenty panels changed between r3 and r4. Their recoverability differs completely — and that difference is the whole feature.
4 manufactured
£720
must be re-made
2 planned
£0
just re-queue
1 installed
escalate
standing in a building
A tool that shows all seven as equally "affected" reproduces the £430-per-build waste it exists to prevent. The only story that surfaced money was marked Should.
Firmware v4.2 event schema contract
Three separate blockers turn out to be one missing document. What the controller must emit was never written down — only what it must do.
FM-4 buffer and reconcile
Blocked → fully fixed
a2 e-stop audit log
Buildable now → improved
a3 per-axis stop timing
Needs a new event type
One document, three blockers, three different resolutions — I was wrong to say it fixed all three. It must be agreed before boards land in week 3, because there is no v4.3 before the demo.
Both findings came from running the fixture data rather than reading the briefs.
Notes: The IW-L1-01 detail is worth having ready: its height changed 2700 to 2750 but weightKg stayed at 85, while every other resized panel had weight recalculated. Someone edited by hand. Nobody asked for that check; it falls out of the diff for free.
Two things went in that weren't in the hand-over, and both fell out of running the fixtures rather than reading the briefs. Four panels genuinely need re-making; two just need re-queueing for nothing; one is standing in a building. And three separate blockers turned out to be one document nobody had written.

## Slide 7
5
What I built, and why not the obvious one
The brief asks for one slice. The second settles an architectural disagreement in code.
SLICE 1 · PYTHON · 157 TESTS
E-stop audit and stop-response
Inspection actions a2 and a3
a2 is the first link in the chain that gates the unsupervised demo.
a3 had no owner — the hand-over reads "Not agreed".
Sits across the software/robotics boundary, where a lead should be.
Records a ≤1s resolution limit rather than false precision. Per-axis deltas are not derivable: six axes, one event, one timestamp.
SLICE 2 · TYPESCRIPT · 66 TESTS
Revision impact and cost
Stories PR-1 and PR-6
The money is in classification, not detection.
A pure function over two whole builds — no schema mutation.
If it works without previousSpec, that argument is over.
The alternative was adding revision and previousSpec to PanelSpec, which supports diffing only one step back and would need rewriting at cutover. A pure function needs neither.
Not built: the telemetry buffer (not buildable on the current schema — the deliverable was the contract), any UI (Sam's work), estimation tooling (ships nothing on 12 Oct).
Notes: Option 6, the run-state machine, was the closest runner-up. Rejected because its central question — what a remote stop does to a half-made panel — is already answered by the sample stream: the cell stops mid-panel and resumes from_panel_start. It costs one panel.
"The brief asks for one slice. I took a2 and a3 because a3 had no owner and sat on the critical path — that's a lead's job, not a volunteer's. The second slice exists to settle an architectural disagreement with a passing test instead of a meeting. Can I show you it running?"

## Slide 8
6
The assumptions that carry weight
Each written so it can be proved wrong. Ten in the plan; these four decide the outcome.
A1
a3's measurement comes from Chris's rig, not from v4.2 firmware timing
IF WRONG
The chain cannot complete before 12 Oct. Unsupervised is off, full stop.
A2
Deploying v4.2 after the cell re-test would invalidate it
IF WRONG
This is why the firmware splits at all. If the inspector only cares about measured behaviour, the whole ordering problem shrinks.
A4
Boards clear supplier testing and arrive in week 3
IF WRONG
Firmware slips 1:1. Plan A has one day of float, so a week's slip forces Plan B.
A10
Sam's two surfaces are about six weeks combined
IF WRONG
My number, not his — inferred from comparable backlog items. Largest single unknown in the capacity table.
Notes: A2 is the one to volunteer. It is the assumption the entire firmware split rests on, and it is answerable with a phone call to the inspector rather than a design decision by me.
"There are ten assumptions in the plan; these four decide the outcome. Each one is written so it can be proved wrong — if it can't be, it's a preference wearing a suit. A2 is the one I'd most like answered, and it's a phone call to the inspector rather than a design decision by me."

## Slide 9
7
Day one
What happens in week one, with owners and dates. Nothing here waits on a decision.
Q-A + Q-B to Chris
Selects Plan A or Plan B before anyone builds against either.
Chris
Fri wk 1
Circulate the v4.2 event schema contract
Must be agreed before boards land. There is no v4.3.
Lead → Chris
Fri wk 1
Start a2 — build slice 1
First link in the chain. Also de-risks scheduling rig time.
Lead
Day 1
Book the inspector provisionally
Ten working days is the lead time from submission, not from asking.
Lead
Day 1
Get Sam's breakdown + refreshed mocks
Two of three user-facing surfaces are currently unplanned work.
Sam, Robin
Fri wk 1
Freeze PanelSpec; publish BuildModel types
Stops the migration surface growing today. Costs nothing.
Jo, Alex
Wk 1
Notes: The point of this slide is that the plan does not stall waiting for answers. Six things start immediately, and the two questions that select the plan are answered inside week one.
None of this waits on a decision. Six things start immediately, and the two questions that select the plan get answered inside week one. The point is that the plan doesn't stall while I'm waiting for anybody.

## Slide 10
8
Where I am least sure
Named before you name them. In order of exposure.
The firmware split is my invention
I proposed v4.2a/v4.2b from a principle — never change the safety configuration after the re-test, only add observability. I do not know embedded release practice. A robotics lead may say firmware does not decompose that way, or that two builds cost more validation than they save. The principle is sound; the mechanism may not be.
Sam's estimates are mine, not his
Inferred from comparable backlog workstreams. It is the largest number in the capacity table and I invented it.
Alex's 1.55× multiplier rests on four data points
And I used it to justify cutting his work.
"Bench validation halves because the scope halves"
An assumption about someone else's job. Plan A dies without it.
Slice 2 tests the diff core, not the integration
So it disproves previousSpec, but it does not prove Alex's four weeks is wrong.
Notes: Do not rush this slide. Naming your own weak points frames them; leaving them costs you the framing. The firmware split is genuinely the most exposed thing in the plan and saying so first is the strongest move available.
I'd rather name these than have you find them. In order of exposure — and the first one is genuinely the most exposed thing in the whole plan. The firmware split is my invention; the principle behind it is sound, but the mechanism may not survive contact with someone who actually ships embedded releases.

## Slide 11
9
Where to push me
The calls I would most like to be argued out of.
Am I right to move the cutover to Q4?
The principle that half-migrated is worse than either end is correct. I am betting the calendar beats the principle for eight weeks — and I have not seen the read paths.
Is PR-6 scope creep dressed as insight?
I added a Must story in week one, having never met the production manager. Robin may have good reasons the cost model is harder than £180 a panel.
Should a2 really start on day one?
Once the firmware chain is admitted, a2 has nine days of float. Starting it immediately may be conservatism I have justified after the fact.
Is two slices one too many?
The brief said pick one, and keep it small. I built two and wrote nine documents.
Have I over-trusted a 29-event sample?
Several decisions rest on one truncated stream from March, which Chris warned has a different cadence.
Notes: Say plainly that these are real questions, not rhetorical ones. If they push on the two-slices point, the honest answer is that slice 2 exists to settle the previousSpec disagreement with a passing test rather than an argument.
These are the calls I'd most like to be argued out of, and they're real questions rather than rhetorical ones. Every one of them is somewhere I made a decision without the person it affects in the room. Where would you start?
## Slide 11 — drafted replies
**How to answer all five:** concede the real part first, then give the case.
Leading with the defence makes a genuine question sound like an attack you're
parrying. Every one of these has something true in it.
---
### 1. Am I right to overrule Jo on the cutover?
"Jo's principle is correct — half-migrated *is* worse than either end, and I'd
argue the same thing in Jo's position. The disagreement isn't the principle,
it's whether it survives this calendar. Jo has 2.8 weeks of capacity before a
target that needs 4.5, and is away weeks four and five, so the week-three
cutover isn't a plan — it's a wish. And a single-PR cutover landing week seven
with seven weeks of new code on top is exactly the outcome Jo is warning about.
Where I'm weak: I've never seen the read paths and Jo has. That's why the
read-path inventory is week-one work — it's a day, and if the remainder is under
1.5 weeks then Jo's plan works and my adapter is over-engineering. The adapter
is two days and gets deleted at cutover, so the insurance is cheap either way."
---
### 2. Is PR-6 scope creep dressed as insight?
"Fair challenge, and I'd push back on one word: I didn't add scope, I moved it.
PR-5 already existed — surfacing cost before approval — it was just marked
*Should*. The whole business case is a money number, so shipping the mechanism
without it leaves the production manager exactly where she is today, with a
tidier list.
The fixture makes it concrete: two of the seven changed panels cost nothing to
fix. A tool that shows all seven as equally affected reproduces the waste it was
funded to prevent.
Where I'm weak: I promoted a Must story having never met the person who'd use
it. If Robin tells me she already knows the cost model well enough to decide
from status alone, I'd drop it — she does this by hand today, so that's
entirely plausible."
---
### 3. Should a2 really start on day one?
"Honestly — probably, but not for the reason I first gave. My original argument
was that a2 is the binding constraint. Once I admitted the firmware chain, that
stopped being true: a2 and a3 carry about nine working days of float. So the
first justification was wrong and I'd rather say that than defend it.
The reasons that survive are weaker but real. a3 needs rig time from Chris, who
is 0.8 FTE and on the commissioning site one day a week — scheduling it is
harder than doing it. And a2/a3 was the unowned work in the pack; picking it up
on day one is as much a signal as a schedule item.
If Chris says rig time books easily, the urgency drops and a2 could start in
week two at no cost."
---
### 4. Is two slices one too many?
"Probably, yes — and this is the weakest of my calls on volume.
The case for the second is that it isn't extra engineering for its own sake. It
settles the Alex-versus-Jo schema disagreement with a passing test instead of a
meeting, which is a leadership move rather than a coding one. If I can hand Alex
a working `classifyRevision(previous, next)` that never touches `previousSpec`,
that argument is over without anyone losing it.
But the brief said pick one and keep it small, and 223 tests across two slices
plus nine documents is not small. If part of what you're testing is whether I
can scope down under time pressure, I didn't pass that. I'll be straight about
my incentive too — in an interview I'd rather be asked why so much than why so
little, and that's my interest, not the company's. In a real week one, the
second slice waits."
---
### 5. Have I over-trusted a 29-event sample?
"Yes, in places — and Chris warned me. His words were 'same event shape,
different cadence.'
The split I'd draw: the *structural* findings hold regardless of cadence. Two
legitimate `nailing.started` events for the same panel, no sequence number, no
clock authority — those are schema defects and they'd still be true in a
thousand-event stream.
What I shouldn't have leaned on: buffer sizing, mean panel cycle, and the
`cycleSeconds` reconciliation. I caveated the buffer number and then quoted it
anyway. And the 388-second cycle drives a UI requirement — the stop wait-state
countdown — off three panels, two of which report *identical* cycleSeconds,
which smells synthetic. One real run in week two settles all three."
---
### 6. Volunteer this one — I under-weighted Q-B
"One I'd add. I framed Q-B as being about Fleet Monitor's integration time, and
it's bigger than that. Under Plan A, v4.2b deploys 1–2 October and sign-off
lands on the 7th — so it isn't landing after the inspector signs, it's landing
*during* their review window, after they have our evidence.
If run events ride in the early half, v4.2b never touches the cell before the
demo and that problem disappears entirely. So Q-B decides whether we modify the
machine while it's under review, not just how much integration time we get.
That's a stronger argument for Plan B than the one on slide 4 — Plan B carries
no version bet at all."

## Slide 12
REFERENCE
Appendices
The working behind the numbers in the deck. Held back so the argument stays short — jump to one when a question needs it.
A
Capacity arithmetic
Where 35.6 person-weeks against 23.9 comes from, person by person.
slide 13
B
What r3 → r4 actually contains
The seven changed panels, their status, and what each one costs.
slide 14
C
Estimation calibration
Per-discipline multipliers, and why bimodal uncertainty is not wide uncertainty.
slide 15
D
Robotics resource pass
Five findings from laying the work out by resource instead of by person.
slide 16
E
What is wrong with the event stream
The five defects behind the firmware schema contract.
slide 17
Notes: Do not present these. This slide exists so you can say 'that is in appendix C' and get there in one move.

## Slide 13
A
Capacity arithmetic
Nominal 24 person-weeks. Actual 23.9 after the calendar, against 35.6 of demand.
Person
Nominal
Bank hol
Offsite
Away
Available
Alex
8.0
−0.2
−0.4
—
7.4
Sam
8.0
−0.2
−0.4
—
7.4
Jo
8.0
−0.2
−0.4
−2.0
5.4
Lead (50% to leading)
8.0
−0.2
−0.4
—
3.7
Total
23.9
Robotics: 2 people, Chris at 0.8, minus ~1 day/week live cell support ≈ 1.6 FTE effective. Their constraint is the single spare controller and the live cell, not headcount — see appendix D.

## Slide 14
B
What r3 → r4 actually contains
Seven of twenty panels changed. All on level 1. Recoverability differs completely.
Panel
Change
Status
Class
Cost
EW-L1-N1
opening x 1200→1800
installed
escalate
TBC
EW-L1-E1
opening x 1800→2400
manufactured
remake
£180
EW-L1-W1
width 4800→4200
manufactured
remake
£180
IW-L1-01
height 2700→2750, weight unchanged
manufactured
remake + suspect
£180
FC-01
span 4800→4200
manufactured
remake
£180
EW-L1-N2
opening x 600→900
planned
requeue
£0
FC-02
span 4800→4200
planned
requeue
£0
Alex's adjacency rule would flag all thirteen level-1 panels — £2,340 if acted on, against a baseline where ~12% of panels are currently wasted. EW-L2-W1 is still 4800 wide while the wall beneath it shrank to 4200: one real defect, which adjacency buries among twelve false ones.

## Slide 15
C
Estimation calibration
Twelve workstreams over two quarters. Ratio of actual to estimate.
Discipline
Non-hardware
Hardware-dependent
Sample
Solver (Alex)
1.55×
2.18×
4 workstreams
Platform (Jo)
1.51×
2.10×
5 workstreams
Frontend (Sam)
1.14×
1.60×
3 workstreams
All
1.42×
2.04×
12 workstreams
Hardware dependency roughly doubles the overrun, consistently, across every discipline.
The bias is not uniform across people. Alex wrote the most detailed plan and Sam wrote "few weeks of work", so Alex looks more rigorous. On the evidence, Alex's numbers need challenging and Sam's need extracting.
Bimodal ≠ wide. Alex's one Low-confidence estimate was two estimates with no way to tell which applies. Padding is wrong in both worlds; the remedy is a timeboxed spike on the deciding fact — and that fact was already answered by the fixtures.

## Slide 16
D
Robotics resource pass
Laid out by resource rather than by person. Found five things and reversed a recommendation.
1
v4.2b had no validation or deploy in the plan
Roughly a week of resource time that existed nowhere.
2
The split starves Fleet Monitor of real data until 2 Oct
First contact with real cell data is the week before the demo.
3
The rehearsal window halves
Two weeks becomes one — the same week as that integration.
4
People pinch, 16–25 Sep
2.5 person-weeks needed against 2.4 available.
5
Plan A's robotics chain has one day of float
15 working days of serial work in 16. The smallest overrun in the backlog history is 13%.
Capacity was never the problem — ~12.1 person-weeks available against ~4.9 of work. Everything above is ordering.

## Slide 17
E
What is wrong with the event stream
Evidence from cell-events.jsonl — 29 events, March trials.
No unique event identifier
nailing.started for EW-L1-E1 appears twice, 07:14:51 and 07:20:05. Both legitimate — the second follows an e-stop resume. Any content-based dedupe drops a real event.
No sequence number
A gap is undetectable. A quiet cell and a thirty-minute outage look identical. The story asks for "no gaps"; today you cannot observe one.
Whole-second timestamps
stop.requested 07:15:33 → motion.halted 07:15:34. a3's measurement is capped at 1s, and same-second events are unorderable.
No clock authority
An NTP step or a reboot mid-outage moves timestamps backwards. Ordering a reconciled buffer by ts is unsafe.
run.paused is overloaded
reason "estop" and reason "material_reload" share one event type. An audit log must distinguish safety from routine.
Required envelope: eventId · seq · bootId · millisecond ts · monotonicUs · class. Plus at-least-once delivery with idempotent receive. Buffer sizing is trivial once the schema is right — the difficulty was never volume.